## Schedule
Lifecycle Stage | Sub-Stage | System | Activity | Description | Activity Duration | System Duration | Sub-Stage Duration | Stage Duration | Assignee
Development | Concept Validation | General | Develop Concept Validation Testing Procedure | Create document to lay out testing protocol | 0.5 Weeks | 9 Weeks | 9 Weeks | 65 Weeks | Overall Team
|  |  | Design Prototype for Concept Validation | Developing theory for how design will function | 1 Week
|  |  | Procure Necessary Material for Prototype | Determing materials within budget from BOM to order | 2 Weeks
|  |  | Construct Prototype | Physically putting together parts | 2 Weeks
|  |  | Perform Concept Validation Testing | Verifying parts can all power on and function | 2 Weeks
|  |  | Generate Testing Report | Writing report on progress and results | 1 Week
|  |  | Finalize Bench Testing Procedure | Documenting steps of testing project sub-systems | 0.5 Weeks
| Initial Documentation | General | Begin the outline for O&M Manual | Work on O&M manual as progress on project is made | Continuous | - | -
|  |  | Document work and progress | Document work and key information for various project documents
| Bench Testing | Frame | Design Rolling Frame | Design frame with Fusion360 | 1 Week | 3.25 Weeks | 28 Weeks |  | Mechanical Lead
|  |  | Procure Necessary Frame Materials | Determing materials within budget from BOM to order | 0.25 Weeks
|  |  | Construct Rolling Frame Prototype | Putting together material to create frame | 2 Weeks
|  | Bend Radius | Design Bend Radius Sub-System | Laying out tasks and workflow | 0.25 Weeks | 6.5 Weeks |  |  | Sensor Sub-System Lead
|  |  | Develop BR Algorithm | Developing theory for code | 1 Week
|  |  | Generate BR Source Code | Writing source code | 1 Week
|  |  | Test/Debug Source Code | Fixing or adding onto source code | 2 Weeks
|  |  | Procure BR Material | Determing materials within budget from BOM to order | 0.25 Weeks
|  |  | Construct BR Sub-System | Physically putting together parts | 1 Week
|  |  | Perform Preliminary Testing | Verifying function with electronics debugging equipment | 1 Week
|  | Scanner | Design Scanner Sub-System | Laying out tasks and workflow | 0.25 Weeks | 5.5 Weeks |  |  | LiDAR Sub-System Lead
|  |  | Develop Scanning Algorithm | Developing theory for code | 1 Week
|  |  | Generate Scanner Source Code | Writing source code | 1 Week
|  |  | Test/Debug Source Code | Fixing or adding onto source code | 1 Week
|  |  | Procure Scanner Material | Determing materials within budget from BOM to order | 0.25 Weeks
|  |  | Construct Scanner Sub-System | Physically putting together parts | 1 Week
|  |  | Perform Preliminary Testing | Verifying function with electronics debugging equipment | 1 Week
|  | Super Elev. | Design SE Sub-System | Laying out tasks and workflow | 0.25 Weeks | 3 Weeks |  |  | Sensor Sub-System Lead
|  |  | Develop SE Algorithm | Developing theory for code | 0.25 Weeks
|  |  | Generate SE Source Code | Writing source code | 0.25 Weeks
|  |  | Test/Debug Source Code | Fixing or adding onto source code | 0.25 Weeks
|  |  | Procure SE Material | Determing materials within budget from BOM to order | 0.25 Weeks
|  |  | Construct SE Sub-System | Physically putting together parts | 0.75 Week
|  |  | Perform Preliminary Testing | Verifying function with electronics debugging equipment | 1 Week
|  | Enclosure + PCB | Generate System Schematics | Drawing up electrical connections between electrical parts | 0.25 Weeks | 3 Weeks |  |  | PCB Sub-System Lead
|  |  | Generate Main PCB Schematics/Layout | Design PCB within Fusion360 | 0.5 Weeks
|  |  | Lay Out Enclosure Components | Develop list of components | 0.25 Weeks
|  |  | Procure Enclosure Material | Determing materials within budget from BOM to order | 0.25 Weeks
|  |  | Construct Enclosure | Putting together PCB with enclosure | 1 Weeks
|  |  | Perform Power Consumption Analysis | Calculating power consumption based on all electronics | 0.5 Weeks
|  |  | Perform Preliminary Testing | Ensure that components are correctly installed to power on and work | 0.25 Weeks
|  | UI | Design UI Sub-System | Laying out tasks and workflow | 0.25 Weeks | 3.5 Weeks |  |  | UI Sub-System Lead
|  |  | Develop UI Algorithm | Developing theory for code | 0.25 Weeks
|  |  | Generate UI Source Code | Writing source code | 1 Week
|  |  | Test/Debug Source Code | Fixing or adding onto source code | 2 Week
|  | General | Construct Full System | Putting together all sub-systems | 0.25 Weeks | 3.25 Weeks |  |  | Overall Team
|  |  | Perform Bench Testing | Testing the design | 2 Weeks
|  |  | Generate Bench Testing Report | Writing report on progress and results | 1 Week
| Performance Testing | System Functionality | Develop Functionality Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks | 14 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
|  | System Accuracy | Develop Accuracy Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
|  | System Repeatability | Develop Repeatability Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
|  | System Usability | Develop Usability Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
| Validation Testing | Measurement Accuracy | Develop Accuracy Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks | 14 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
|  | Measurement Repeatability | Develop Repeatability Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
|  | System Reliability | Develop Reliability Testing Protocol | Planning what will be done to perform thorough testing | 0.5 Weeks | 3.5 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debug Issues/Refine Design | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
|  | Edge-Case Avoidance | Develop Edge-Case Protocol | Determing what extreme cases to test our system against (severe curve radii, low illumination, etc) | 0.5 Weeks | 3.5 Weeks
|  |  | Perform Field Testing | Testing on a field at a train yard or inside a tunnel | 1 Week
|  |  | Debugging Edge Case Issues | Fixing errors or adding features in electrical/mechanical/software design | 2 Weeks
Implementation | Pilot Program | Pilot Program Prep | Find main point of contact for field testing | Strategize with Chris for finding lead person to coordinate pilot program | 0.25 Week | 1 Week | 9 Weeks | 20.5 Weeks
|  |  | Identifying trainees and setting expectations | Working with lead person to identify field engineers to test design | 0.75 Week
|  | Kickoff and Training Documentation | Drafting training manual | Laying out and writing document structure | 1 Week | 2 Weeks
|  |  | Revising/Finalizing for training manual | Receiving feedback from within TCIG and CoE for implementation | 0.75 Weeks
|  |  | Approval | Receive appropriate sign-off | 0.25 Weeks
|  | Pilot Program Field Testing | Guided training and system use | Creating schedule training relevant stakeholders on the field | 1 Week | 6 Weeks
|  |  | Unguided system use | Giving relevant stakeholders unsupervised time with the system | 2 Weeks
|  |  | Analysis | Reviewing end user experience | 1 Week
|  |  | Recap Meetings/Feedback | Meeting with lead person and trainees to get feedback | 1 Week
|  |  | Implementing feedback/improvements | Implementing worthwhile suggestions | 1 Weeks
| Documentation | Operation & Maintenance Manual | Determining Individual Sensor Lifetimes | Researching parts and datasheets to gauge lifetime | 1 Week | 6.5 Weeks | 11.5 Weeks
|  |  | Determing Calibration Requirements | Researching parts and datasheets to calibration requirements | 1 Week
|  |  | Defining Roles for Maintenance | Using sensor research to determine who needs to perform calibration | 0.5 Weeks
|  |  | Establishing Maintenance Schedule | Using sensor research to determine maintenance frequency | 0.5 Weeks
|  |  | Introducing O&M Manual to Key Roles | Meeting with key roles to talk about O&M Manual and transferring it to them | 0.5 Weeks
|  |  | Drafting | Laying out and writing document structure | 1 Week
|  |  | Revising | Receiving feedback within TCIG, from field engineers, PMs, etc | 1 Week
|  |  | Finalizing/Approval | Implementing final edits and receiving appropriate sign-off | 1 Week
|  | Implementation Report | Drafting | Laying out and writing document structure | 2 Weeks | 5 Weeks
|  |  | Revising | Receiving feedback within TCIG, from field engineers, PMs, etc | 2 Weeks
|  |  | Finalizing/Approval | Implementing final edits and receiving appropriate sign-off | 1 Week
Control & Monitoring | Documentation | Finalizing White Paper | Drafting | Laying out and writing document structure | 2 Weeks | 6 Weeks | 11 Weeks | 11 Weeks
|  |  | Revising | Receiving feedback within TCIG, from field engineers, PMs, etc | 2 Weeks
|  |  | Finalizing/Approval | Implementing revisions and receiving appropriate sign-off | 2 Weeks
|  | Closeout Report | Drafting | Drafting final report for Chris | 2 Weeks | 5 Weeks
|  |  | Revising | Revisions made within TCIG | 2 Weeks
|  |  | Finalizing/Approval | Getting Chris's approval | 1 Week